## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name | [5 empty] | Initials | Student ID
Required | Che Justus Kwanga | [6 empty] | 1001671827
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 24 |  |  |  | Total | Total number of features (in column H)
1 | 21 | 3 |  |  | 1 | Total features left at the end of Sprint #1
2 | 21 | 0 |  |  | 2 | Total features left at the end of Sprint #2
3 | 19 | 2 |  |  | 3 | ...and so on
4 | 17 | 2
5 | 4 | 13
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
EXIT | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | User | Exit the GUI program (File > Exit) | Use it again another day | Baseline an existing project’s code for class Mainwin, main function, and Makefile from e.g., MUSS (P6 – recommended), Nim (13), or Paint (17). Pare down GUI to what’s definitely reusable. Requires Mainwin::on_quit_click.
DOG | 2 | 1 |  | 21 | 1 | Finished in Sprint 1 | Staff | Create a new dog (Animal > New) | Track dogs seeking good homes | Requires Mainwin::on_create_animal; 1 dialog; classes Animal and Dog; Shelter::add_animal and attributes; and enum classes Gender and Dog_breed
LANIM | 3 | 1 |  | 5 | 1 | Finished in Sprint 1 | Staff | List animals (Animal > List Available) | See what animals are available | Requires Shelter::num_animals and animal; and Mainwin::on_animals_list; probably operator<< for dog
CAT | 4 | 2 |  | 8 | 2 | Finished in Sprint 3 | Staff | Create and list cats as well | Also put cats up for adoption | Requires class Cat; 1 Mainwin dialog to select Dog or Cat for Animal > New; and enum class Cat_breed; probably operator<< for Cat
RABBIT | 5 | 2 |  | 8 | 2 | Finished in Sprint 3 | Staff | Create and list rabbits as well | Also put rabbits up for adoption | Requires class Rabbit; and enum class Rabbit_breed; probably operator<< for Rabbit
CLIENT | 6 | 2 |  | 13 | 2 | Finished in Sprint 3 | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mainwin::on_create_client; 1 dialog; class Client; Shelter::add_client and attributes
LCLIENT | 7 | 3 |  | 5 | 3 | Finished in Sprint 3 | Client | List clients (Client > List) | See which clients are available | Requires Shelter::num_clients and client; and Mainwin::on_clients_list
ADOPT | 8 | 3 |  | 5 | 3 | Finished in Sprint 4 | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Client::adopted vector and Client::adopt method; 1 dialog
LADOPT | 9 | 3 |  | 8 | 3 | Finished in Sprint 4 | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires Client::num_adopted and animal methods; 1 dialog to select the client; Mainwin::on_list_adopted_click
SAVE | 10 | 4 |  | 13 | 4 | Finished in Sprint 4 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal::save, Dog::save, Cat::save, and Rabbit::save; Shelter::save; Shelter::filename with getter and setter; and Mainwin::on_save_click
LOAD | 11 | 4 |  | 5 | 4 | Finished in Sprint 4 | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal::Animal(ist), Dog::Dog, Cat::Cat, and Rabbit::Rabbit; Shelter::Shelter; and Mainwin::on_open_click; dialog and logic for handling “dirty” data (baseline and adapt from Paint(17) if you don’t have it already)
NEW | 12 | 5 |  | 5 | 5 | Finished in Sprint 5 | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mainwin::on_new_shelter_click;
SAVEF | 13 | 5 |  | 5 | 5 | Finished in Sprint 5 | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mainwin::on_save_as_click; Shelter::set_filename; adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already); set filename in Shelter
LOADF | 14 | 5 |  | 5 | 5 | Finished in Sprint 5 | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | If the current data is unsaved, display a custom dialog asking whether to save it, discard it, or cancel, and respond accordingly. Requires adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already).
ABOUT | 15 | 5 |  | 2 | 5 | Finished in Sprint 5 | Director | Display version and required attributions (Help > About) | Stay legal and in control | Requires adding Mainwin::on_about_click with Gtk::AboutDialog. Include a properly licensed logo!
PHOTO | 16 |  | 32 | 8 | 5 |  | Client | See photo and information about an available animal (Animal > View) | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.
NANIM | 17 |  | 20 | 5 | 5 |  | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
ROLE | 18 |  | 52 | 13 | 5 |  | Director | Select role with authentication and selected sensitivity (Role > Client, Staff, Manager, and Director) | Limit features to appropriate users | Add _role attribute to Shelter. Add “Select Role” dialog (Client, Staff, Manager, and Director) with preset password validation (except Client), set sensitivity of menu items and buttons per User_Interface_Full.pdf
PROP | 19 |  | 20 | 5 | 5 |  | Manager | Display Shelter properties (File > Properties...) | Monitor Shelter operation | In a custom dialog, display the name of the shelter, number of clients, number of available animals of each type, and number of adopted animals
UNDO | 20 |  | 32 | 8 | 5 |  | Staff | Undo a change to the Shelter records (Edit > Undo) | Correct errors | Stack of Undo objects should track ONLY new animal (remove the animal from available), new client (remove the client from the list of clients), and adoptions (move animal from client back to available), Requires Undo object with pointer to one animal and one client; implementation is obvious.
RANIM | 21 |  | 12 | 3 | 5 |  | Staff | See all animals the shelter has encountered (Report > Animals) | Estimate the shelter’s impact | No additional dialogs required, but must iterate through all clients to assemble addopted animals with those on available vector
RCLIENT | 22 |  | 8 | 2 | 5 |  | Staff | See all clients and the animals they have adopted in a single report (Report > Clients) | Quickly find an adopted animal | No additional dialogs required, but must iterate through all clients to assemble data including adopted animals. Very similar to Report > Animals.
STAFF | 23 |  | 84 | 21 | 5 |  | Director | Maintain explicit lists of staff, managers, and directors (Edit > Staff, Manager, and Director) | Manage shelter operation | Derive a Staff class from Client, adding enum class Role (staff, manager, director), salary, and password. Create edit dialog to modify this data, selecting from list, with a New button to create new staff member. Modify Role > (role) password to validate against named staff’s unique password.
ACTIVE | 24 |  | 32 | 8 | 5 |  | Manager | Set clients, staff, directors, and managers “inactive”, and restore to “active” | Retain staffing info even when staff is on leave or quits | Add an _active bool, default true, to Staff class, and add to the edit dialog. Filter out inactive staff members from all ComboBoxText and similar selections EXCEPT the edit dialog (so they can be reactivated). Don’t allow inactive staff to log in.

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2019-10-29 |  | CHE JUSTUS KWANGA
End on | 2019-11-05
Demo on | 2019-12-03
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 3 | 0
Day 2 Left | 3 | 0
Day 3 Left | 3 | 0
Day 4 Left | 3 | 0
Day 5 Left | 3 | 0
Day 6 Left | 2 | 1
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | User | Exit the GUI program (File > Exit) | Use it again another day | Baseline an existing project’s code for class Mainwin, main function, and Makefile from e.g., MUSS (P6 – recommended), Nim (13), or Paint (17). Pare down GUI to what’s definitely reusable. Requires Mainwin::on_quit_click.
2 |  |  | Staff | Create a new dog (Animal > New) | Track dogs seeking good homes | Requires Mainwin::on_create_animal; 1 dialog; classes Animal and Dog; Shelter::add_animal and attributes; and enum classes Gender and Dog_breed
3 |  |  | Staff | List animals (Animal > List Available) | See what animals are available | Requires Shelter::num_animals and animal; and Mainwin::on_animals_list; probably operator<< for dog
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2019-11-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 3 | 0
Day 2 Left | 3 | 0
Day 3 Left | 3 | 0
Day 4 Left | 3 | 0
Day 5 Left | 3 | 0
Day 6 Left | 3 | 0
Day 7 Left | 3 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Create and list cats as well | Also put cats up for adoption | Requires class Cat; 1 Mainwin dialog to select Dog or Cat for Animal > New; and enum class Cat_breed; probably operator<< for Cat
2 |  |  | Create and list rabbits as well | Also put rabbits up for adoption | Requires class Rabbit; and enum class Rabbit_breed; probably operator<< for Rabbit
3 |  |  | Create a new client (Client > New) | Track candidate adopters | Requires Mainwin::on_create_client; 1 dialog; class Client; Shelter::add_client and attributes
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2019-11-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 2
Day 1 Left | 2 | 0
Day 2 Left | 2 | 0
Day 3 Left | 2 | 0
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 1 | 1
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Client | List clients (Client > List) | See which clients are available | Requires Shelter::num_clients and client; and Mainwin::on_clients_list
2 |  |  | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Client::adopted vector and Client::adopt method; 1 dialog
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2019-11-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-11-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 2
Day 1 Left | 2 | 0
Day 2 Left | 2 | 0
Day 3 Left | 2 | 0
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 1 | 1
Day 7 Left | 0 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal::save, Dog::save, Cat::save, and Rabbit::save; Shelter::save; Shelter::filename with getter and setter; and Mainwin::on_save_click
2 |  |  | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal::Animal(ist), Dog::Dog, Cat::Cat, and Rabbit::Rabbit; Shelter::Shelter; and Mainwin::on_open_click; dialog and logic for handling “dirty” data (baseline and adapt from Paint(17) if you don’t have it already)
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2019-11-26 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2019-12-03
Demo on | 2019-12-05
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 9 | 4
Day 2 Left | 9 | 0
Day 3 Left | 9 | 0
Day 4 Left | 9 | 0
Day 5 Left | 9 | 0
Day 6 Left | 9 | 0
Day 7 Left | 9 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mainwin::on_new_shelter_click;
2 |  |  | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mainwin::on_save_as_click; Shelter::set_filename; adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already); set filename in Shelter
3 |  |  | Load the data from a specified file (File > Open) | Work with multiple shelters | If the current data is unsaved, display a custom dialog asking whether to save it, discard it, or cancel, and respond accordingly. Requires adding Gtk::FileChooserDialog (baseline from Paint(17) if you don’t have it already).
4 |  |  | Display version and required attributions (Help > About) | Stay legal and in control | Requires adding Mainwin::on_about_click with Gtk::AboutDialog. Include a properly licensed logo!
5 |  |  | See photo and information about an available animal (Animal > View) | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.
6 |  |  | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
7 |  |  | Select role with authentication and selected sensitivity (Role > Client, Staff, Manager, and Director) | Limit features to appropriate users | Add _role attribute to Shelter. Add “Select Role” dialog (Client, Staff, Manager, and Director) with preset password validation (except Client), set sensitivity of menu items and buttons per User_Interface_Full.pdf
8 |  |  | Display Shelter properties (File > Properties...) | Monitor Shelter operation | In a custom dialog, display the name of the shelter, number of clients, number of available animals of each type, and number of adopted animals
9 |  |  | Undo a change to the Shelter records (Edit > Undo) | Correct errors | Stack of Undo objects should track ONLY new animal (remove the animal from available), new client (remove the client from the list of clients), and adoptions (move animal from client back to available), Requires Undo object with pointer to one animal and one client; implementation is obvious.
10 |  |  | See all animals the shelter has encountered (Report > Animals) | Estimate the shelter’s impact | No additional dialogs required, but must iterate through all clients to assemble addopted animals with those on available vector
11 |  |  | See all clients and the animals they have adopted in a single report (Report > Clients) | Quickly find an adopted animal | No additional dialogs required, but must iterate through all clients to assemble data including adopted animals. Very similar to Report > Animals.
12 |  |  | Maintain explicit lists of staff, managers, and directors (Edit > Staff, Manager, and Director) | Manage shelter operation | Derive a Staff class from Client, adding enum class Role (staff, manager, director), salary, and password. Create edit dialog to modify this data, selecting from list, with a New button to create new staff member. Modify Role > (role) password to validate against named staff’s unique password.
13 |  |  | Set clients, staff, directors, and managers “inactive”, and restore to “active” | Retain staffing info even when staff is on leave or quits | Add an _active bool, default true, to Staff class, and add to the edit dialog. Filter out inactive staff members from all ComboBoxText and similar selections EXCEPT the edit dialog (so they can be reactivated). Don’t allow inactive staff to log in.
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84